## Change Request Info
This document is prepared by : | Balaji S | Version | 12th October 2020
CHANGE SUMMARY
SPC Ticket Number | CR686108
HCM ServiceNow Ticket Number
Change Description | Cluster switch upgrade for Cisco switch NX3132V from 7.0(3)I4(1) version to 7.0(3)I7(8) in cluster hec08fc001
Other reference tickets (If Applicable) | Please Input Descriptions (e.g. Accenture SNOW) ServiceNow Ticket) |  |  | Please input the ticket ID
| Please Input Descriptions (e.g. Verizon Noc #) |  |  | Please input the ticket ID
Data Center (include all DCs impacted here) | SAP-HEC-SydneySydney 1 (SY3)
RISK ASSOCIATED WITH THE CHANGE |  |  |  |  | LOW
We have categorized this change as low, as we have redundancy for cluster switch level . While one cluster switch is performing upgrade its HA partner will serve the data.
BUSINESS JUSTIFICATION
what will business get once this change is done, or project deliverables descriptions :In Risk report, Cisco cluster-switch risk has been identified which have risk “Switch might get stuck and can no longer forward packets“. To resolve the issue, it is require to upgrade the cluster switch OS version to 7.0(3)I7(8). what is the impact if the change is not approved by CIS CAB, or : The cluster switch will be exposed to bugs on existing version mentioned in the auto support risk which might lead Switch to get stuck and can no longer forward packets
Note on A11: This shall be a text description of the risks involved.
Note on A15: This is a complete sentence that describes the business impact in terms that are easy to understand (no technical terms).

## Detailed Impact to LoB
This tab must be filled for Disruptive RfCs impacting HEC
HEC - CUSTOMER CONNECTION IMPACT (to be filled for disruptive changes only)
Customer Connection type | Affected
MPLS with 2 cables with non - dynamic routing
MPLS with 2 cables and BGP
MPLS with only 1 cable
VPN
Internet connection
Load Balancer scenarios
Connection between systems
SAP internal connection to 2nd DC
Cloud Peering – Single Connection
Cloud Peering – Redundant Connection
Special Instructions to be communicated to CUSTOMERS (if any)
Note on B8: Mark the affected connections with 'X'
Note on A20: Provide information in case other activities than reporting an incident in the unlikely event of any irregularity is required.

## CIs to be changed
Please enter into below table the target devices / Configuration items for this change
Devices for the Change
Datacenter | Device Name | Console device name | Mgmt IP Address | Management Port | Has Redundant Setup ? | Redundant Device Name | Device Type | Serial Number | Rack | RU | please feel free to add more coloumns if additional information is needed.
SAP-HEC-Sydney(Sydney 2,SYD10) | hec08fc001 |  | 198.18.238.8/23 | e0M
| hec08f0011 |  | 198.18.238.30/23 | e0M | Yes | hec08f0011 | AFF-A700s | 941806000205 | Sydney2-S120-R07-2_RU 37
| hec08f0012 |  | 198.18.238.31/23 | e0M | Yes | hec08f0012 | AFF-A700s | 941809000103 | Sydney2-S120-R07-2_RU 35
| hec08f0013 |  | 198.18.238.32/23 | e0M | Yes | hec08f0013 | AFF-A700s | 941810000050 | Sydney2-S120-R07-2_RU 27
| hec08f0014 |  | 198.18.238.33/23 | e0M | Yes | hec08f0014 | AFF-A700s | 941810000045 | Sydney2-S120-R07-2_RU 25
| hec08f0015 |  | 198.18.238.43/23 | e0M | Yes | hec08f0015 | AFF-A700s | 941836000186 | Sydney2-S120-R07-2_RU 23-26
| hec08f0016 |  | 198.18.238.44/23 | e0M | Yes | hec08f0016 | AFF-A700s | 941834000193 | Sydney2-S120-R07-2_RU 23-26
| hec08f0017 |  | 198.18.238.51/23 | e0M | Yes | hec08f0017 | AFF-A700s | 951950000314 | APJ-au-SYD10 syd2 S120-7-2-19
| hec08f0018 |  | 198.18.238.52/23 | e0M | Yes | hec08f0018 | AFF-A700s | 951950000115 | APJ-au-SYD10 syd2 S120-7-2-17
|  | hec08f0011 | 198.18.224.132 |  |  |  | BMC
|  | hec08f0012 | 198.18.224.133 |  |  |  | BMC
|  | hec08f0013 | 198.18.224.134 |  |  |  | BMC
|  | hec08f0014 | 198.18.224.135 |  |  |  | BMC
|  | hec08f0015 | 198.18.224.95 |  |  |  | BMC
|  | hec08f0016 | 198.18.224.96 |  |  |  | BMC
|  | hec08f0017 | 198.18.224.26 |  |  |  | BMC
|  | hec08f0018 | 198.18.224.27 |  |  |  | BMC
| hec08fc001cs03 |  | 198.18.238.36 |  |  |  | NX3132V | FOC2148R183
| hec08fc001cs04 |  | 198.18.238.37 |  |  |  | NX3132V | FOC2147R1BJ

## Impacted CIs
Impacted Configuration Items (CI) | [6 empty] | List all the impacted CI technical info so that we can decide the impacts of the changes.
Type of CI | Details | Descriptions | LOBs | Contact Name | Disruption Expected | Redundancy Available | Comments | please feel free to add more coloumns if additional infor is needed.
VLAN | vlan ID | more info associated to the CI | add LOB if known | add LOB contact if known | yes/no | yes/no | add specific points
IP network | 10.0.0.0/22
LIF | LIF IP
Port
URL
VM names
add rows when needed

## Topology Diagram
Please include here technical diagram (Before and After) whenever applicable

## Cabling Requirements
Please include here cabling requirements if applicable, or attach completed DCM cabling work template here ==>
Migration Only
Data Centre | Point A Rack | Point A RU | Point A Device Name | Point A Port | Point B Rack | Point B RU | Point B Device | Point B Port | Interface type | Cable Length | New Point A Rack | New Point A RU | New Point A Device | New Point A Port | Comments

## Detail Execution Plan
If any pre-check or validation steps fails highlight in "RED" the step in which backout/rolllback will be considered. Backout or rollback should be factored in the GCS CAB Approved Implementation Timeframe.
Detailed Execution Tasks
1. Pre-check & Preparation Steps
Phase | Step No. | Task Description | Expected Duration of Implementation Duration (in mins.) | Disruptive / Non Disruptive | Describe Natual and Expected Duration of Disruption | Detailed Technical tasks/commands/screenshots | Comments
1. Pre-check & Preparation Steps | 1 | "Time Required - 15 mins 1. Display information about the devices in your configuration: >network device-discovery show | 15 | Non Disruptive | NONE | network device-discovery show -discovered-device hec08fc001cs3 -fields node,port,interface,discovered-device network device-discovery show -discovered-device hec08fc001cs4 -fields node,port,interface,discovered-device |  | Please include * detailed pre-check criteria * planned actions if the pre-check fails (highlight them in red)
| 2 | DXC Engineer to run pre-check health checks script as per the enviornment and it should be attached in change request. |  | Non Disruptive | NONE
| 3 | Determine the administrative or operational status for each cluster interface: >network port show -role cluster |  | Non Disruptive | NONE | network port show -role cluster
| 4 | Display information about the logical interfaces: >network interface show -is-home false |  | Non Disruptive | NONE | network interface show -is-home false
| 5 | Display the information on the discovered cluster switches: >system cluster-switch show |  | Non Disruptive | NONE | system cluster-switch show
| 6 | Verify the cluster's health: >network interface show -role cluster |  | Non Disruptive | NONE | network interface show -role cluster
| 7 | Ping the remote cluster interfaces and perform an RPC server check: >cluster ping-cluster |  | Non Disruptive | NONE | cluster ping-cluster -node hec08f0011 cluster ping-cluster -node hec08f0012 cluster ping-cluster -node hec08f0013 cluster ping-cluster -node hec08f0014 cluster ping-cluster -node hec08f0015 cluster ping-cluster -node hec08f0016 cluster ping-cluster -node hec08f0017 cluster ping-cluster -node hec08f0018
| 8 | DXC storage engineer to check health with regards to the Databases in advance mode ::>set advanced Warning: These advanced commands are potentially dangerous; use them only when directed to do so by NetApp personnel. Do you want to continue? {y¦n}: y ::*>cluster ring show All the RDB's should be in sync with same value of each node. Normally these are in sync but incase of issue we will log case with NetApp. |  | Non Disruptive | NONE | cluster ring show
| 9 | DXC storage engineer to check health status of the cluster. |  | Non Disruptive | NONE | storage failover show
| 10 |  |  | Non Disruptive | NONE
| 11 |  |  | Non Disruptive | NONE
| 12 |  |  | Non Disruptive | NONE
| 13 |  |  | Non Disruptive | NONE
| 14 |  |  | Non Disruptive | NONE
2. Implementation Steps
Phase | Step No. | Action | Expected Duration of Implementation Duration (in mins.) | Disruptive / Non Disruptive | Describe Natual and Expected Duration of Disruption
2. Implementation Steps | 1 | "Time required - 1hr Total Number of Nodes: 2 Switches Time Require per node: 30 Mins |  | Non Disruptive | NONE |  |  | Please include * detailed validation steps and validation criteria, when required during the implementation phase * planned actions if the validation fails (highlight them in red), refer to rollback plan section for different rollback scenario when applicable
| 2 | Migrate the LIFs associated with the cluster ports connected to switch hec07fc001cs3 >network interface migrate -vserver <cluster_name> -lif <lif_name> -source-node <node_name> –destinationnode <node_name> -destination-port <port> |  | Non Disruptive | NONE | net int migrate -vserver Cluster -lif hec08f0011_clus1 -destination-node hec07f0011 -destination-port e0f net int migrate -vserver Cluster -lif hec08f0012_clus1 -destination-node hec07f0012 -destination-port e0f net int migrate -vserver Cluster -lif hec08f0013_clus1 -destination-node hec07f0013 -destination-port e0f net int migrate -vserver Cluster -lif hec08f0014_clus1 -destination-node hec07f0014 -destination-port e0f net int migrate -vserver Cluster -lif hec08f0015_clus1 -destination-node hec07f0015 -destination-port e0f net int migrate -vserver Cluster -lif hec08f0016_clus1 -destination-node hec07f0016 -destination-port e0f net int migrate -vserver Cluster -lif hec08f0017_clus1 -destination-node hec07f0017 -destination-port e0f net int migrate -vserver Cluster -lif hec08f0018_clus1 -destination-node hec07f0018 -destination-port e0f
| 3 | Shut down the cluster interconnect ports that are physically connected to switch hec07fc001cs3: >network port modify -node <node_name> -port <port> -up-admin false | 30 | Non Disruptive | NONE | network port modify -node hec07f0011 -port e0a -up-admin false network port modify -node hec07f0012 -port e0a -up-admin false network port modify -node hec07f0013 -port e0a -up-admin false network port modify -node hec07f0014 -port e0a -up-admin false network port modify -node hec07f0015 -port e0a -up-admin false network port modify -node hec07f0016 -port e0a -up-admin false network port modify -node hec07f0017 -port e0a -up-admin false network port modify -node hec07f0018 -port e0a -up-admin false
| 4 | Ping the remote cluster interfaces and perform an RPC server check: >cluster ping-cluster -node <node_name> >network interface show -role cluster |  | Non Disruptive | NONE | cluster ping-cluster -node hec07f0011 cluster ping-cluster -node hec07f0012 cluster ping-cluster -node hec07f0013 cluster ping-cluster -node hec07f0014 cluster ping-cluster -node hec07f0015 cluster ping-cluster -node hec07f0016 cluster ping-cluster -node hec07f0017 cluster ping-cluster -node hec07f0018
| 5 | Verify the current contents of the bootflash: >dir bootflash: |  | Non Disruptive | NONE | dir bootflash:
| 6 | Download the NX-OS image of NX-OS to hec07fc001cs3 copy scp://root@<server Ip from where need to copy the image>/<Path where image file resides>/nxos.7.0.3.I7.8.bin bootflash |  | Non Disruptive | NONE | https://software.cisco.com/download/home/286305588/type/282088129/release/7.0(3)I7(8)?i=!pp Copy the image to bootflash location by using scp command copy scp://root@<server Ip from where need to copy the image>/<Path where image file resides>/nxos.7.0.3.I7.8.bin bootflash
| 7 | 6. Install the kickstart and system image so that the new version will be loaded upon the next switch reboot. During the image installation, the install procedure might determine that the switch has to be powered off. If so, power off the switch, wait for five seconds, and then power it up again before proceeding to the next step. >install all nxos bootflash:nxos.7.0.3.I7.8.bin |  | Non Disruptive | NONE | install all nxos bootflash:nxos.7.0.3.I7.8.bin (During the image installation, the install procedure might determine that the switch has to be powered off. If so, power off the switch, wait for five seconds, and then power it up again before proceeding to the next step.) ( Local DC smarthand support engineer will be availabile at the site during change window of the cluster switch upgrade activity and will be performing the above mentioned steps. )
| 8 | Save the configuration, and then reboot hec07fc001cs3 >copy running-config startup-config >reload |  | Non Disruptive | NONE | copy running-config startup-config reload (This command will reboot the system. (y/n)? [n] press yes) If any issues occurred during the reboot , Local DC smart hands support engineer to be available at the site during the change window of cluster switch upgrade and the Engineer manually reboot the cluster switch )
| 9 | Confirm that the new NX-OS version number is on the switch. >show version |  | Non Disruptive | NONE | show version
| 10 | On all nodes, bring up all of the cluster interconnect ports connected to switch hec07fc001cs3 >network port modify -node <node_name> -port <port> -up-admin true |  | Non Disruptive | NONE | network port modify -node hec07f0011 -port e0a -up-admin true network port modify -node hec07f0012 -port e0b -up-admin true network port modify -node hec07f0013 -port e0a -up-admin true network port modify -node hec07f0014 -port e0b -up-admin true network port modify -node hec07f0015 -port e0a -up-admin true network port modify -node hec07f0016 -port e0a -up-admin true network port modify -node hec07f0017 -port e0a -up-admin true network port modify -node hec07f0018 -port e0a -up-admin true
| 11 | For all nodes, revert all of the migrated cluster interconnect LIFs: >network interface revert -vserver <cluster_name> -lif <lif_name> |  | Non Disruptive | NONE | net int revert -vserver Cluster -lif hec08f0011_clus1 net int revert -vserver Cluster -lif hec08f0012_clus1 net int revert -vserver Cluster -lif hec08f0013_clus1 net int revert -vserver Cluster -lif hec08f0014_clus1 net int revert -vserver Cluster -lif hec08f0015_clus1 net int revert -vserver Cluster -lif hec08f0016_clus1 net int revert -vserver Cluster -lif hec08f0017_clus1 net int revert -vserver Cluster -lif hec08f0018_clus1 net int revert -vserver Cluster -lif hec07f0017_clus1
| 12 | Ping the remote cluster interfaces and perform an RPC server check: >cluster ping-cluster >network interface show -role cluster |  | Non Disruptive | NONE | cluster ping-cluster -node hec07f0011 cluster ping-cluster -node hec07f0012 cluster ping-cluster -node hec07f0013 cluster ping-cluster -node hec07f0014 cluster ping-cluster -node hec07f0015 cluster ping-cluster -node hec07f0016 cluster ping-cluster -node hec07f0017 cluster ping-cluster -node hec07f0018
| 13 | Verify that all of the cluster ports are up: >network port show –role cluster |  |  |  | network port show –role cluster
| 14 | Repeat this procedure to upgrade the NX-OS software and RCF on hec07fc001cs4 |  | Non Disruptive | NONE | Step2-14(Repeat this procedure to upgrade the NX-OS software and RCF on hec08fc001cs4 and cluster port e0a
| 18 |  |  | Non Disruptive | NONE
| 19 |  |  | Non Disruptive | NONE
| 20 |  |  | Non Disruptive | NONE
| 21 |  |  | Non Disruptive | NONE
| 22 |  |  | Non Disruptive | NONE
23
| 26 |  |  | Non Disruptive | NONE
| 27 |  |  | Non Disruptive | NONE
| 28 |  |  | Non Disruptive | NONE
| 29 |  |  | Non Disruptive | NONE
| 30 |  |  | Non Disruptive | NONE
3. After implementation Verification/Validation and Post-Activity Steps
Phase | Step No. | Action | Expected Duration of Implementation Duration (in mins.) | Disruptive / Non Disruptive | Describe Natual and Expected Duration of Disruption
3. After implementation Verification/Validation and Post-Activity Steps (Inlcuding business validation) | 1 | Determine the administrative or operational status for each cluster interface: >network port show -role cluster | 15 | Non Disruptive | NONE | network port show -role cluster |  | Please include * detailed validation criteria * planned actions if the validation fails (highlight them in red)
| 2 | Display information about the logical interfaces: >network interface show |  | Non Disruptive | NONE | network interface show
| 3 | Display the information on the discovered cluster switches: >system cluster-switch show |  | Non Disruptive | NONE | system cluster-switch show
| 4 | Verify the cluster's health: >network interface show -role cluster |  | Non Disruptive | NONE | network interface show -role cluster
| 5 | Ping the remote cluster interfaces and perform an RPC server check: >cluster ping-cluster >network interface show -role cluster |  | Non Disruptive | NONE | cluster ping-cluster -node hec07f0011 cluster ping-cluster -node hec07f0012 cluster ping-cluster -node hec07f0013 cluster ping-cluster -node hec07f0014 cluster ping-cluster -node hec07f0015 cluster ping-cluster -node hec07f0016 cluster ping-cluster -node hec07f0017 cluster ping-cluster -node hec07f0018
| 6 | Confirm that the new NX-OS version number is on the switch. >show version |  | Non Disruptive | NONE | show version
| 7 | Perform basic health check on cluster. ::>storage failover show ::>storage failover show -fields auto-giveback,auto-giveback-after-panic (values for both parameters should be false) ::>aggr show (Check aggregates are assigned to their own nodes or not) ::>vol show ::>vol show -state !online (It will display all the volumes which are not in online state) ::>ifgrp show (Check all ports are active in LACP or not) ::>system service-processor show (Check SP status and check SP connectivity status by logging in to SP) ::>system health subsystem show (Check all subsystems Helath status, all should be OK) ::>System health alert show (Check for any alerts.if any alerts are reported,try to fix them first) ::> lun show ::> CIFS show ::> CIFS share show ::> system node image show (Run in advanced mode to see current defult ONTAP image) ::>version -v ::>security config show (Run in advanced mode to see TLS versions) |  | Non Disruptive | NONE | storage failover show (Both HA nodes should be in connected state with takeover possible "true") storage failover show -fields auto-giveback,auto-giveback-after-panic (values for both parameters should be false) aggr show (Check aggregates are assigned to their own nodes or not) vol show vol show -state !online (It will display all the volumes which are not in online state) ifgrp show (Check all ports are active in LACP or not) system service-processor show (Check SP status and check SP connectivity status by logging in to SP) system health subsystem show (Check all subsystems Helath status, all should be OK) System health alert show (Check for any alerts.if any alerts are reported,try to fix them first) lun show CIFS show CIFS share show system node image show version -v security config show (Run in advanced mode to see TLS versions)
| 8 | Perform the cluster health check script and verify event logs for any issue. |  | Non Disruptive | NONE
| 9 |  |  | Non Disruptive | NONE
| 10 |  |  | Non Disruptive | NONE
| 11 |  |  | Non Disruptive | NONE | storage failover show (Both HA nodes should be in connected state with takeover possible "true") storage failover show -fields auto-giveback,auto-giveback-after-panic (values for both parameters should be false) aggr show (Check aggregates are assigned to their own nodes or not) vol show vol show -state !online (It will display all the volumes which are not in online state) ifgrp show (Check all ports are active in LACP or not) system service-processor show (Check SP status and check SP connectivity status by logging in to SP) system health subsystem show (Check all subsystems Helath status, all should be OK) System health alert show (Check for any alerts.if any alerts are reported,try to fix them first) lun show CIFS show CIFS share show system node image show version -v security config show (Run in advanced mode to see TLS versions)
4. Rollback Steps
Phase | Step No. | Action | Expected Duration of Implementation Duration (in mins.) | Disruptive / Non Disruptive | Describe Natual and Expected Duration of Disruption
4. Rollback | 1 | "Time Required - 1 Hour Revert to version 7.0.3.I4 |  | Non Disruptive | NONE |  |  | Please include * detailed validation criteria * please include all scenario of rollback plans (if there are different rollback plans based on the change progress, or situation)
| 2 | Migrate the LIFs associated with the cluster ports connected to switch hec07fc001cs3 >network interface migrate -vserver <cluster_name> -lif <lif_name> -source-node <node_name> –destinationnode <node_name> -destination-port <port> |  | Non Disruptive | NONE
| 3 | Shut down the cluster interconnect ports that are physically connected to switch hec07fc001cs3: >network port modify -node <node_name> -port <port> -up-admin false |  | Non Disruptive | NONE
| 4 | Ping the remote cluster interfaces and perform an RPC server check: >cluster ping-cluster -node <node_name> >network interface show -role cluster |  | Non Disruptive | NONE
| 5 | Verify the current contents of the bootflash: >dir bootflash: |  | Non Disruptive | NONE | dir bootflash:
| 6 | Download the NX-OS image of NX-OS to hec07fc001cs3 Copy the image to bootflash location by using scp command copy scp://root@<server Ip from where need to copy the image>/<Path where image file resides>/nxos.7.0.3.I7.8.bin bootflash |  | Non Disruptive | NONE | https://software.cisco.com/download/home/286305588/type/282088129/release/7.0(3)I4(1) Copy the image to bootflash location by using scp command copy scp://root@<server Ip from where need to copy the image>/<Path where image file resides>/nxos.7.0.3.I4.1.bin bootflash
| 7 | 6. Install the kickstart and system image so that the new version will be loaded upon the next switch reboot. During the image installation, the install procedure might determine that the switch has to be powered off. If so, power off the switch, wait for five seconds, and then power it up again before proceeding to the next step. >install all nxos bootflash:nxos.7.0.3.I7.8.bin |  | Non Disruptive | NONE | install all nxos bootflash:nxos.7.0.3.I4.1.bin (During the image installation, the install procedure might determine that the switch has to be powered off. If so, power off the switch, wait for five seconds, and then power it up again before proceeding to the next step.) ( Local DC smarthand support engineer will be availabile at the site during change window of the cluster switch upgrade activity and will be performing the above mentioned steps. )
| 8 | Save the configuration, and then reboot hec07fc001cs3 >copy running-config startup-config >reload |  | Non Disruptive | NONE | copy running-config startup-config reload (This command will reboot the system. (y/n)? [n] press yes) If any issues occurred during the reboot , Local DC smart hands support engineer to be available at the site during the change window of cluster switch upgrade and the Engineer manually reboot the cluster switch )
| 9 | Confirm that the new NX-OS version number is on the switch. >show version |  | Non Disruptive | NONE | show version
| 10 | On all nodes, bring up all of the cluster interconnect ports connected to switch hec07fc001cs3 >network port modify -node <node_name> -port <port> -up-admin true
| 11 | For all nodes, revert all of the migrated cluster interconnect LIFs: >network interface revert -vserver <cluster_name> -lif <lif_name> |  | Non Disruptive | NONE
| 12 | Ping the remote cluster interfaces and perform an RPC server check: >cluster ping-cluster |  | Non Disruptive | NONE
| 13 | Verify that all of the cluster ports are up: >network port show –role cluster |  | Non Disruptive | NONE | network port show –role cluster
| 14 | Repeat this procedure to upgrade the NX-OS software and RCF hec07fc001cs4 |  |  |  | Step2-14(Repeat this procedure to upgrade the NX-OS software and RCF on hec08fc001cs4 and cluster port e0a

## Contact Info
Change Execution Contact Details | [5 empty] | add rows when necessary
IMPLEMENTATION RESOURCE CONTACT DETAILS
Serial | Name | Team | Email | Phone Number
1 | Abishek Sugavalvu | DXC Storage Team | abishek.sugavalvu@sap.com | 7090016427
3
4
5
VALIDATION RESOURCE CONTACT DETAILS
Serial | Name | Team | Email | Phone Number
1 | Ashok Kandimalla | DXC Storage Team | ashok.kandimalla@sap.com | +918019411077
2
3
4
5
ROLLBACK RESOURCE CONTACT DETAILS
Serial | Name | Team | Email | Phone Number
1 | Abishek Sugavalvu | DXC Storage Team | abishek.sugavalvu@sap.com | 7090016427
2
3
4
5
BUSINESS VALIDATION CONTACT INFO
Serial | Name | Team | Email | Phone Number
1
2
3
TECHNICAL ESCALATION MATRIX
Serial | Name | Team | Email | Phone Number
1 | Gaurav Mathur | DXC storage Team | gaurav.mathur01@sap.com | +91 9717 005691
2
Change Coordinator / Project Manager / Managers / Other critical contacts
Serial | Name | Role | Email | On standby | Phone Number
1 | Pulkit Goel | Change -Coordinator/ Storage Team Lead | p.goel@sap.com | Yes | +919899191991

## Revision History (hidden)
This is the revision history of the runbook template
Seq | date | Comments
1 | Sept 12, 2019 | Initial version : 20190912